General Election Work Plans

We need to ratify and launch lines of effort for the general election on the following elements:

- Trump

- Character/trust

- Millennials

This is obviously not an exhaustive list, as we will need evolving work on African-American and Latino voters and women, among others.  But these are three crucial projects we need to get underway now.

This memo seeks to outline the main elements and decision points for each of these lines of effort.

- TRUMP

We need to set up a structure that is capable of executing at both the strategic (defining Trump and the choice between HRC and Trump) and the tactical (rapid response and keeping him off balance).  Christina Reynolds has done a first crack at the many different specific tasks that will be required.  This memo does not cover all of those; rather it covers the key pieces we need to lock in so that the work can get underway in earnest.

Structure:  We envision a Trump task force with:

- An overall captain (Jason Miner, Leslie Dach)

- An opposition research captain (Judd Legum, Brent Colburn)

- An opinion research captain (Navin, with Petts as lead pollster)

- A Republican recruitment captain (?)

- A spokesperson (Leslie Dach or other?)

- A team of behavioral and social psychologists, humorists,  and other experts who can help us think through a totally different kind of candidate (to discuss)

Opinion research timeline:  Attached is a timeline that covers Trump polling and groups, for us to discuss and ratify.

Opposition research timeline:  We will ask our opposition research captain to present us with parameters and a schedule for completing the work.

Political outreach timeline:  We need our Republican outreach captain to develop a timeline for how and through what channels we reach out to Republican electeds, former Republican officials (and former brass who have previously supported Republicans), and Republican-leaning constituencies like community bankers and small business leaders.

Interim approach:  Jen has proposed a dual message frame against Trump and Sanders:  essentially, the three tests from Little Tuesday speech for why HRC is only candidate who can do the job – 1) has solutions that will actually help people; 2) can be CINC; and 3) can bring the country together.  Jen has also proposed that we pursue the idea of using the next batch of states – particularly New York and Pennsylvania – to start the first round of serious Trump contrast.  Having HRC hit Trump more in these states could help secure more decisive victories against Sanders and help define Trump early on. We should look to use New York (where he is best known and most hated) to cast Trump as a bad businessman and lousy to workers.  Part of the thought here is that we can’t let key blocs of voters become invested in him.  We have to disqualify him early with these blocs (independents, women, Hispanics, African Americans and some Republicans).

Decisions:

- Personnel:  Fill in the roles and getting people hired and in place

- Interim approach:  Ratify Jen’s proposal for how to handle Trump over the next few weeks

- Longer-term approach:  Ratify the timelines for the other lines of effort

- CHARACTER/TRUST

We need to be able to identify the root of the “trust” or character issue, and then decide whether (1) we can actually take it on and decrease the “don’t trust her” numbers, or (2) we can redefine trust or character in a way that plays up her record of accomplishment, or (3) we take a dismal trust number as a given and – since we are running against someone with even lower favorables – simply make the case that it doesn’t matter, and what matters instead is the three-part test we’ve set forth.  Once we have decided on our basic objective and approach, we need to develop a strategy across all platforms to accomplish the objective.

Structure:  This effort would fall under the general HRC message process led by Jen and Jake.  Dan Schwerin would run point on the conceptual side of this.  John Anzalone would lead the opinion research aspect.

Opinion research timeline:  Attached is an opinion research timeline that covers character/trust.

Outreach to experts:  Dan will be tasked with leading a process of reaching out to people on methods and devices we might use to address the trust question.  This can include the settings and feel of HRC events, digital and paid media strategies, and interviews and other media opportunities.  This process will be informed by but not totally dictated by the opinion research.

Interim approach:  The six weeks between now and the New York primary offer an opportunity to animate the argument HRC started making in the Ohio town hall about how she is better at being in office than running for office, and that when people put their trust in her she delivers for them.  Jen and Jake can work on a gameplan for how to effectuate this.

Decisions:

- Personnel:  Is Schwerin the right person?

- Opinion research timeline:  Discuss changes to the proposed research timeline

- Interim approach:  Ratify proposal for how to approach this issue between now and April 26

- MILLENNIALS

We need a concerted strategy to bring millennials into the HRC tent in a general election context.  This will require a better understanding of why they are so disenchanted by HRC and how we can repair the breach – assuming there is a way to do so.  It may well be that our main goal will end up being to motivate them against Trump rather than for HRC, but we will obviously have to address both sides of the equation.

Structure:  A millennial team captain will lead and organize the effort across platforms.  Kristina, Navin, and Teddy have been tasked with identifying the right person.  Joel Benenson and his team will lead the opinion research.

Opinion research timeline:  Attached is an opinion research timeline that covers millennials.

Outreach to experts:  Judith McHale and other experts are now engaged, but the millennial team captain will have to lead an inclusive and broad-based process of engaging people outside the campaign to help inform our approach.

Interim approach:  Since Bernie retains such broad appeal with young people, we probably don’t want to invest too heavily in this over the next six weeks.  That said, we should not give them up entirely. We should pursue open town halls geared to millennials as we did in New Hampshire.  We should also begin pursuing some of the media opportunities Teddy has identified in his memo.  We get points for making clear HRC wants to listen to millennials and understand their concerns as they are our next generation of leaders and have them get to know her better – even if they are going to be for  Bernie now.

Decisions:

- Personnel:  Who should lead this effort?

- Opinion research timeline:  Ratify this approach and timeline

- Interim approach:  Do we all agree we are not making a big millennial play in the run-up to the late April primaries, but we are going to layer in some of Teddy’s proposals, including things like millennial town halls and relevant interviews?