## Traditional Calendar
Opinion Research Calendar Through June 7
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2016-03-19
2016-03-20 | 2016-03-21 | 2016-03-22 | 2016-03-23 | 2016-03-24 | 2016-03-25 | 2016-03-26
|  | Election Day: AZ-UT-ID |  |  |  | Election Day: WA-HI-AK
[5 empty] | Brief HRC on Research Plan | Memo on HRC Approach
Research Meeting on Trump & HRC
2016-03-27 | 2016-03-28 | 2016-03-29 | 2016-03-30 | 2016-03-31 | April 1 | 2016-04-02
Debrief on Polls
FIELD HRC
FIELD Trump
FIELD Attack/Response
2016-04-03 | 2016-04-04 | 2016-04-05 | 2016-04-06 | 2016-04-07 | 2016-04-08 | 2016-04-09
|  | Election Day: WI |  |  |  | Election Day: WY
|  | Send Signal |  |  |  | Debrief on Groups
Creative Brainstorm | [5 empty] | Integrate Message
ONLINE GROUPS HRC GE
ONLINE GROUPS Trump
2016-04-10 | 2016-04-11 | 2016-04-12 | 2016-04-13 | 2016-04-14 | 2016-04-15 | 2016-04-16
HRC Briefing on Research to Date
Creative Check-in
FIELD 2nd HRC Message (Oversample Obama Voters)
FIELD 2nd Trump Poll (Obama Voters Only)
2016-04-17 | 2016-04-18 | 2016-04-19 | 2016-04-20 | 2016-04-21 | 2016-04-22 | 2016-04-23
Election Day: NY
Debrief on both polls | [5 empty] | Tentative plan on sequence of GE
|  | Finalize Scripts |  |  | HRC Shoot
FOCUS GROUPS Millenial Online Groups
FOCUS GROUPS Latino GE
FOCUS GROUPS AfAm GE
2016-04-24 | 2016-04-25 | 2016-04-26 | 2016-04-27 | 2016-04-28 | 2016-04-29 | 2016-04-30
Election Day: CT-DE-MD-PA-RI
Debrief on Millenial, Latino, AfAm Groups
HRC Shoot |  | FIELD Millenial Poll
FIELD Latino Poll
FIELD AfAm Poll
2016-05-01 | 2016-05-02 | 2016-05-03 | 2016-05-04 | 2016-05-05 | 2016-05-06 | 2016-05-07
|  | Election Day: IN |  |  |  | Election Day: GUAM
HRC Briefing on Path to Victory
Debrief on Polls
Spots Due
2016-05-08 | 2016-05-09 | 2016-05-10 | 2016-05-11 | 2016-05-12 | 2016-05-13 | 2016-05-14
Election Day: WV
2016-05-15 | 2016-05-16 | 2016-05-17 | 2016-05-18 | 2016-05-19 | 2016-05-20 | 2016-05-21
Election Day: KY, OR
2016-05-22 | 2016-05-23 | 2016-05-24 | 2016-05-25 | 2016-05-26 | 2016-05-27 | 2016-05-28
2016-05-29 | 2016-05-30 | 2016-05-31 | 2016-06-01 | 2016-06-02 | 2016-06-03 | 2016-06-04
Election Day: VIRGIN ISLANDS
2016-06-05 | 2016-06-06 | 2016-06-07 | 2016-06-08 | 2016-06-09 | 2016-06-10 | 2016-06-11
Election Day: PUERTO RICO |  | Election Day: CA, MT, NJ, NM, ND, SD